## Advanced Embedded
1 |  | #Week | 07.05.2022 | 21.05.2022 | 04.06.2022 | 18.06.2022
2 |  | Task | Task 1 | Task 2 | Task 3 | Task 4
3 |  |  | Project: Weather monitoring system | Project: Weather monitoring system | Project: Weather monitoring system | Project: Weather monitoring system
4 | Patrick Nonki | To-do | Research about the project topic, hardware | Research on connecting sensors to RasberryPi and Arduino. | Setting up our RasberryPi with a static ID, SSH setup | Setting up our RasberryPi with a static ID, SSH setup
|  |  | sensors and actuator selection. | Research on connecting DHT11 and Arduino to Raspberry Pi over MQTT. | Work on realising the whole project. | Installing mosquito to raspberryPi
|  |  |  | Overall project planning. |  | Work on realising the whole project.
- Work on documentation of the project and presentation together.
- UML Class Diagram, Sequence and Use-Case diagram.
5 |  | Status | Done | Done | Done | Done
6 | Izuchukwu George Enekwa | Short summary | Research about the project topic, hardware | Research on connecting sensors to RasberryPi and Arduino. | Connecting DHT Sensor, coding and creating MQTT topic to publish the values | - Work on documentation of the project and presentation together.
|  |  | and sensors and actuator selection. | Research on connecting DHT11 and Arduino to Raspberry Pi over MQTT. |  | - Work on realising the whole project.
|  |  |  | - Overall project planning. |  | Setting up Thingspeak as our subscriber
7 |  | To-do | Done | Done | Done | Done
8 | Obi Nnamdi Elijah | Short summary | Research about the project topic, hardware | Research on connecting sensors to RasberryPi and Arduino. | -Connecting Temparature & Humidity Sensor, coding | Work on documentation of the project and presentation together.
|  |  | and sensors and actuator selection. | Research on connecting DHT11 and Arduino to Raspberry Pi over MQTT. | and creating MQTT topic to publish the values | - Work on realising the whole project.
|  |  |  | - Overall project planning. |  | Setting up Thingspeak as our subscriber
9 |  | To do | Done | Done | Done | Done
10 | Abdul Azeez Olanlokun | Short summary | Research about the project topic, hardware | Research on connecting sensors to RasberryPi and Arduino. | -Selecting the rigth motor (stepper motor),coding in | - Creation of Block diagram for Paper and Presenation.
|  |  | and sensors and actuator selection. | Research on connecting DHT11 and Arduino to Raspberry Pi over MQTT. | arduino IDE and creating a topic to subscribe to | - Work on realising the whole project
|  |  |  | - Overall project planning. | and activate it. | - Creating the User interface in the MQTT IOT panel app together
Setting up our RasberryPi with a static ID, SSH setup
11 |  | To-do | Done | Done | Done | Done